## Change Log
ID | Date Received | Client Note (verbatim) | Decoded Change | Feedback Mode | MoSCoW Priority | Round | Status | In Scope? | Notes
1 | 2026-06-01 | Make it pop | Increase contrast on hero headline and add an accent colour to the primary button | Vague | Should | 1 | Done | Yes | Confirmed accent = brand orange
2 | 2026-06-01 | Logo feels cheap | Use calmer navy-led palette, more whitespace around the mark | Vague | Must | 1 | Open | Yes | Decoded as wants more premium
3 | 2026-06-02 | Add three more product photos | Add 3 product images to gallery section | Prescriptive | Could | 2 | Open | No | New scope - quote 1.5 hrs

## Legend
Field | Allowed Values | Meaning
Feedback Mode | Vague / Prescriptive / Contradictory / Scattered | Which failure mode the raw note fits, to pick the right clarifying move
MoSCoW Priority | Must / Should / Could / Will not | Triage priority for the change request
Status | Open / In progress / Done | Current state of the change
In Scope? | Yes / No | No means it is new scope and should be priced or deferred