## Work Breakdown
Task | Milestone | Depends On | Estimate (hrs) | Actual (hrs) | Status
Kickoff and brief review | M1 Discovery |  | 2 |  | Done
Sitemap and content plan | M1 Discovery | Kickoff and brief review | 4 |  | In Progress
Wireframes for 5 page types | M1 Discovery | Sitemap and content plan | 8 |  | Backlog
Client review round 1 | M1 Discovery | Wireframes for 5 page types | 0 |  | Waiting On Client
Home page design | M2 Design | Client review round 1 | 10 |  | Backlog
Inner page templates (4) | M2 Design | Home page design | 12 |  | Backlog
Client review round 2 | M2 Design | Inner page templates (4) | 0 |  | Backlog
Build and content population | M3 Launch | Client review round 2 | 14 |  | Backlog
Cross-device testing | M3 Launch | Build and content population | 4 |  | Backlog
Final revisions and launch | M3 Launch | Cross-device testing | 6 |  | Backlog
Project buffer (end of project) | M3 Launch |  | 12 |  | Reserved

## Milestones and Payments
Milestone | Client-Visible Result | Target Date | Payment % | Status
M1 Discovery | Approved wireframes | 2026-07-10 | 40 | On track
M2 Design | Approved page designs | 2026-07-24 | 30 | Not started
M3 Launch | Live, signed-off website | 2026-08-07 | 30 | Not started

## Change Log
Date | Request | Revision or New Scope | Time Impact (hrs) | Cost / Trade | Agreed
2026-07-12 | Tweak homepage hero wording | Revision (round 1) | 1 | Included | Yes
2026-07-15 | Add a blog section (5 templates) | New scope | 10 | Quoted +$650 | Pending
2026-07-18 | Third full design direction | New scope | 8 | Beyond 2 rounds, billed hourly | Pending