## Hierarchy
Space | Folder (optional) | List | What it represents | Access (everyone / selected) | Default view
Client Work | Acme | Design | Acme design tasks | selected | Board
Client Work | Acme | Development | Acme build tasks | selected | List
Client Work | Bolt | Content | Bolt content pipeline | selected | Calendar
Internal Ops |  | Hiring | Recruiting pipeline (Folderless) | selected | Board
Internal Ops |  | Finance | Invoices and budget (Folderless) | selected | Table

## Statuses
Order | Status name | Group (Not Started / Active / Done / Closed) | Set at (Space or List) | Exit criteria (when a task may move on)
1 | Backlog | Not Started | Space | Top item is detailed enough to start
2 | In Progress | Active | Space | Work is finished and ready to hand off
3 | Ready for Review | Active | Space | A reviewer pulls it
4 | In Review | Active | Space | Approved or sent back with notes
5 | Complete | Done | Space | Definition of done met; archive after one week