## Tasks
Task | Owner | Start date | Due date | Priority | Effort | Status | Waiting on (predecessor) | On critical path?
Finalize sitemap | Sam | Week 1 Mon | Week 1 Fri | High | 3 | On track |  | Yes
Write copy | Priya | Week 1 Wed | Week 2 Wed | High | 5 | On track | Finalize sitemap | Yes
Design page | Lee | Week 2 Thu | Week 3 Fri | High | 5 | At risk | Write copy | Yes
Build page | Dev team | Week 4 Mon | Week 4 Fri | High | 8 | Not started | Design page | Yes
QA on staging | Sam | Week 5 Mon | Week 5 Thu | Medium | 3 | Not started | Build page | Yes
Flip DNS and announce | Lee | Week 6 Mon | Week 6 Mon | High | 2 | Not started | QA on staging | Yes