## Deliverables Matrix
Deliverable | Quantity | Format / Files | Acceptance Criteria (definition of done) | Client Dependency | MoSCoW | Milestone
Homepage copy | 1 page, up to 600 words | Shared doc: headline, subhead, 3 sections, CTA | Reflects approved voice, includes 3 key messages, fits wireframe sections | Approved brand voice guide | Must | M1 Content
Primary logo | 1 logo, 3 variations | SVG, PNG, PDF; source files on final payment | Meets approved concept direction; legible at 32px and on dark/light | Brand brief and references | Must | M2 Design
Social templates | 4 templates | Editable source plus exported PNG | Match approved logo and palette; correct platform dimensions | Final logo approved | Should | M3 Assets
Favicon | 1 set | ICO and PNG at standard sizes | Renders cleanly at 16px and 32px | Final logo approved | Could | M3 Assets
Print-ready files | Out of scope | n/a | n/a | n/a | Won't (this phase) | Future

## Payment Schedule
Milestone | Trigger / Definition of Done | Amount (USD) | % of Total | Due (net days) | Status
Deposit | Signed SOW and contract | 1750 | 50% | Before work starts | Required to begin
M1 Content approved | Homepage copy meets acceptance criteria | 875 | 25% | Net 14 | Pending
Final delivery | All Must and Should deliverables accepted | 875 | 25% | Net 14, before file transfer | Pending
Total project fee | Sum of milestones | 3500 | 100%
Late fee | Per month on overdue invoices | 1.5% |  | Accrues after due date | Per contract

## Exclusions & Assumptions
Type | Item | Notes / Rate if Added
Exclusion | Printing and print management | Quoted separately if requested
Exclusion | Hosting setup and domain | Client responsibility
Exclusion | Copywriting beyond homepage | Out-of-scope rate 95/hr
Exclusion | Stock photography licenses | Billed at cost plus handling
Assumption | Client supplies brand assets by M1 date | Delay shifts timeline
Assumption | One named decision-maker, 2-day feedback turnaround | Slower feedback extends schedule
Assumption | Client owns or has licensed all supplied material | Warranted in contract