## Onboarding Steps
Step | Owner | Due (relative to signing) | Status | Notes
Agreement signed, deposit invoice sent | You | Day 0 | Done | Official start of onboarding
Instant confirmation message | You | Within 2 hours | Done | Thank-you plus next-step preview
Deposit cleared | Client | By day 3 | Pending | No work begins before this
Welcome packet delivered | You | Within 24 hours | Pending | PDF or shared link
Intake questionnaire sent | You | On deposit cleared | Pending | Due 2 days before kickoff
Asset and access request | Client | 2 days before kickoff | Pending | One destination, chase if missing
Workspace and tools set up | You | Before kickoff | Pending | Folder, project hub, calendar
Kickoff meeting held | Both | Within 5 business days | Pending | Agenda sent in advance
Recap sent and confirmed | You | Within 1 day of kickoff | Pending | Get reply to confirm
First work block begins | You | After recap confirmed | Pending | Set first checkpoint date

## Asset and Access
Item | Format Needed | Requested | Received | Notes
Logo files | Vector (SVG, AI, EPS) | Yes | No | Not a screenshot
Brand guidelines | PDF | Yes | No | Colors, fonts, usage
Copy and content | Doc or shared link | Yes | No | Final, sign-off complete
System access or login | Direct invite | Yes | No | Avoid shared passwords
References and competitors | Links | Yes | No | Like and dislike, with why
Internal approvals | Confirmation | Yes | No | Needed before work begins

## Client Pipeline
Client / Project | Onboarding Stage | Deposit Paid | Intake Returned | Kickoff Date | Status
Brewhouse Coffee Rebrand | Kickoff scheduled | Yes | Yes | 2026-07-08 | On track
Acme Startup Website | Awaiting deposit | No | No |  | Invoice sent
Local Bakery Identity | Intake out | Yes | No |  | Chasing assets
Monthly Social Retainer | Onboarded | Yes | Yes | 2026-06-30 | Active