## Deliverables
Deliverable | Category | Final Size | Colour Mode | Bleed / Safe | File Format | Vendor | Due Date | Status
Conference programme | Print | A5 booklet, 16pp | CMYK | 3mm bleed / 5mm safe | PDF/X-1a | Print shop | T-minus 14 days | In progress
Attendee badge | Print | 4 x 3 in, double-sided | CMYK | 3mm bleed / 4mm safe | PDF/X + data merge | Badge printer | T-minus 7 days | Template built
Entrance banner | Large-format | 8 x 3 ft | CMYK | Vendor spec + pole pockets | Vector PDF | Signage vendor | T-minus 10 days | Not started
Stage backdrop | Large-format | 20 x 10 ft | CMYK / LED | Camera safe zone | Vector PDF | AV / set vendor | T-minus 10 days | Not started
Holding slide loop | Screen | 1920 x 1080 | RGB | Title-safe 90% | MP4 + PDF | AV team | T-minus 3 days | Not started
Speaker announcement card | Social | 1080 x 1080 | RGB | n/a | PNG / Canva | Marketing team | Rolling | Template built

## Sponsor Tiers
Sponsor | Tier | Logo Width (Programme) | Backdrop Placement | Screen Reel Slots | Clear Space | Logo File Received
Example Corp | Platinum | 60mm | Top row, large | 3 per loop | 1x logo height | Vector received
Sample Ltd | Gold | 40mm | Mid row | 2 per loop | 1x logo height | PNG only, chase vector
Demo Inc | Silver | 28mm | Lower row | 1 per loop | 0.5x logo height | Not received

## Sign Schedule
Sign ID | Type | Message | Location | Size | Substrate | Mounting | Min Letter Height
S-01 | Identification | Registration | Main entrance | A1 | Foamex | A-frame | 3 in
S-02 | Directional | Main Hall -> / Breakouts -> | Lobby fork | A2 | Foamboard | Easel | 2 in
S-03 | Orientation | You are here floor plan | Lobby + Level 2 | A0 | Vinyl on board | Wall-mounted | 1 in
S-04 | Regulatory | Fire exit | All corridors | A3 | Rigid PVC | Wall-mounted | 1.5 in