## Campaign Brief
Field | Your Answer
Cause / organisation | Riverside Community Food Bank
Priority audience | Local supermarket shoppers aged 30 to 60 who pass the collection point
SOCO (one action) | I want local shoppers to drop three tins in the Saturday collection trolley
Real barrier | They forget at the moment, and are unsure exactly what to give
Single thought | Three tins from your trolley feeds a neighbour this week
Outcome metric + target | Tins collected on Saturday; target 1,200 vs 700 baseline
Frame chosen (gain/loss + why) | Gain framing; donating is a safe, positive prevention behaviour
One human story / face | Maria, a pensioner the food bank supports, with consent

## Theory of Change
Link | Description | Assumption That Must Hold | Risk (High/Med/Low) | Cheap Test
Inputs | 10 design hours, 50 dollar print budget, store permission | Store agrees to display the sign at the entrance | Med | Confirm with store manager before printing
Activities | A3 trolley sign plus a shelf-edge prompt listing three needed tins | Shoppers notice the sign on the way in | Med | Observe foot-traffic and eye level for 30 minutes
Outputs | Roughly 2,000 shoppers see the sign on Saturday | Footfall on Saturday matches the store's estimate | Low | Ask the store for typical Saturday counts
Outcomes | Shoppers drop tins in the trolley | The ask is easy and specific enough to act on now | High | Test wording with five shoppers for clarity
Impact | More food parcels delivered to isolated residents | Donated items match what parcels actually need | Low | Check the food bank's current shortage list

## Measurement
Metric | Type (Output/Outcome) | How Tracked | Baseline | Target | Actual
Tins collected Saturday | Outcome | Weighed and counted at close | 700 | 1,200
Shoppers reached | Output | Store footfall estimate | n/a | 2,000
New monthly donors | Outcome | Sign-up sheet with how-heard question | 0 | 15