## Agenda
Time | Topic | Lead | What is needed (decision / update / input) | Desired outcome
0:00 | Wins since last meeting | Chair | Update | Shared picture of progress
0:05 | Focus for this week | Each member | Update | Everyone knows the priorities
0:15 | Decision: launch date | Project lead | Decision | A date everyone commits to
0:22 | Blockers to raise | Anyone | Input | Owner assigned to each blocker
0:27 | Recap and actions | Chair | Decision | Decisions read back, actions assigned

## Actions
Action (verb-first) | Owner | Due date | Status | In Planner?
Confirm the launch date with the agency | Account lead | Tue | Open | Yes
Draft the launch announcement | Priya | Thu | Open | Yes
Update the reporting dashboard | Analyst | Fri | Open | Yes
Unblock the asset approval | Manager | Wed | Open | Yes