## AAR Record
AAR ID | Project / Event | Date of AAR | Facilitator | Participants | What Was Supposed to Happen | What Actually Happened | Key Gap | Root Cause (Systemic) | Action Item | Owner | Deadline | Outcome Metric
AAR-001 | Q2 product launch | 2026-06-10 | Operations Lead | Core team (6) | Launch by June 1 with 500 signups in week 1 | Launched June 8; 310 signups week 1 | Delayed by 7 days; 38% below signup target | Email sequence not loaded into automation tool — no handoff checklist between marketing and ops | Create a pre-launch handoff checklist | Marketing Lead | 2026-06-17 | Checklist used on next launch

## Action Tracker
AAR ID | Action Item | Owner | Deadline | Status | Completion Date | Impact Observed
AAR-001 | Create pre-launch handoff checklist | Marketing Lead | 2026-06-17 | Open