## Tasks
Task | Assignee | Start date | Due date | Status | Priority | Effort | Time estimate (hrs) | Waiting on (predecessor) | On critical path?
Finalize sitemap | Sam | Week 1 Mon | Week 1 Fri | In Progress | High | 3 | 6 |  | Yes
Write copy | Priya | Week 1 Wed | Week 2 Wed | To Do | High | 5 | 10 | Finalize sitemap | Yes
Design page | Lee | Week 2 Thu | Week 3 Fri | To Do | High | 5 | 12 | Write copy | Yes
Build page | Dev team | Week 4 Mon | Week 4 Fri | To Do | High | 8 | 20 | Design page | Yes
QA on staging | Sam | Week 5 Mon | Week 5 Thu | To Do | Normal | 3 | 8 | Build page | Yes
Flip DNS and announce | Lee | Week 6 Mon | Week 6 Mon | To Do | High | 2 | 2 | QA on staging | Yes